## Sheet1
Key activity | Source of Key Activity | Strategic Plan containing required actions | Lead Officer accountable for progress | Key Actions required to meet the recommendation | Date actions required by | Performance measure to be used to demonstrate progress
1. The monitoring of the implementation of the Looked After Children and Care leavers Strategy | Ofsted Inspection (June 2015) - Item 1 - Nottinghamshire Post Inspection Improvement Plan - Octoer 2015 | Looked After Children and Care Leavers Strategy | Dawn Godfrey, Group Manager, Social Work Services | The Strategy's supporting action plan is implemented successfully and timely, and meets the requirements of the Ofsted Improvement Plan including the following specific actions: (1) All care leavers have a health passport by time they leave care (LAC and Care Leavers Strategy Annual Action Plan) (2) Health Audit to be completed (Children in Care Health Pathway Action Plan) (3) IROs to raise the profile of Health Passports by confirming if LAC have them and reporting these findings on a 6-montly basis (4) Review CAMHS LAC Commissioning to include service to care leavers | (1) End of March 2016 (2) End of June 2016 (3) End of Oct 2015 (4) End of December 2015 | * Percentage of care leavers who have their ‘Important Health Information Pack’ (health passport) at point of leaving care. * CAMHS LAC Service is extended to provide advice and support to care leavers. * Percentage of pathway plans graded good or better in audits undertaken through the Quality Management Framework * Average Strengths and Difficulties Questionnaires (SDQ) Score per LAC. * Percentage of LAC with up to date immunisations * Percentage of LAC who have had their teeth checked by a dentist
2. The gathering and use of management information pertaining to care leavers who are missing, at risk of sexual exploitation, substance misusers or offenders, to understand needs and allocate resources. | Ofsted Inspection (June 2015) - Item 3 - Nottinghamshire Post Inspection Improvement Plan - Octoer 2015 | Help and Protection Plan | Dawn Godfrey, Group Manager, Social Work Services Jon Hawketts, Group Manager, Quality and Improvement | (1) Implement tick boxes within Pathway Plans on Framework for each risk area (2) Business Objects report to be developed to extract risk areas to support the management oversight of individual cases. | (1) End of October 2015 (2) End of December 2016 | * Individual risks are identified, recorded and reviewed as part of the Pathway planning process * Business Objects reports are available to support casework
3. The implementation, monitoring and review of the 16+ accommodation strategy and engage with providers, district and borough councils to drive improvements. | Ofsted Inspection (June 2015) - Item 4 - Nottinghamshire Post Inspection Improvement Plan - Octoer 2015 | Help and Protection Plan | Dawn Godfrey, Group Manager; Social Work Services Laurence Jones, Group Manager, Early Help | (1) Produce practice guidance on support for care leavers with Housing Leads in District Councils through the Youth Homelessness Forum (2) Produce a revised three year Youth Homelessness Strategy incorporating the new outcomes framework and plans to support care leavers with accommodation | (1) End of March 2016 (2) End of June 2016 | * Improvements in outcomes for care leavers and 16/17 year old homeless in supported accommodation settings using the agreed outcomes framework
4. The collection and analysis of information about the effectiveness and impact of the council’s arrangements for services to children and young people who receive early help are improved to better inform practice and service development. | Ofsted Inspection (June 2015) - Item 7 - Nottinghamshire Post Inspection Improvement Plan - Octoer 2015 | Help and Protection Plan | Laurence Jones, Group Manager, Early Help Jon Hawketts, Group Manager, Quality and Improvement | (1). For early help and social care information to be combined into a single report so that the journey of children through the system are better understood (2). For a network of practitioners able to provide intelligence to support data analysis and to suggest service improvement of data to be established (3). For outcome measures for early help services to be reviewed to ensure they best represent the impact of services | (1) Single report to be produced for Q3 (2015-16) (2) End of December 2015 (3) December 2015 | * Revised outcome measures included in the Early Help Service Plan for 2015-2016
5. The improvement of mental health services for vulnerable children and young people (including the implementation of Section 136 of the Mental Health Act 1983 in relationship to children and young people in Nottinghamshire). | Ofsted Inspection (June 2015) - Item 10 - Nottinghamshire Post Inspection Improvement Plan - Octoer 2015 | Children and Young People's Mental Health and Wellbeing Tranformation Plan | Gary Eves, Senior Public Health and Commissioning Manager, Integrated Commissioning Hub | (1) Work with Nottinghamshire Heathcare Trust (NHFT) to implement plan to reduce waiting times (2) Develop a CAMHS Crisis Response and Extended Treatment Service (3) Implement action plan to ensure no young person on S136 are detained in Police custody suites | End of June 2016 | (1) The waiting time from referral to treatment (2) Response made within four hours of referral (3) Numbers of young people detained; discharged within 24 hours; conveyance
6. Children's Services including schools are able to meet the requirements of the 'Prevent Duty' | Safer Notts Board / Prevent Duty for Schools (July 2015) | Help and Protection Plan | Steve Edwards, Service Director, Children's Social Care John Slater, Service Director, Education Standards and Inclusion | To develop an action plan for CFCS and schools to support the delivery of the Prevent Duty, which complements the Emerging Threats to Children Project and the proposed School Health Hub | End of March 2016 | * CFCS 'Prevent Duty' action plan delivered including the appropriate training and guidance for the workforce, and the establishment of clear pathways for referrals.
7. The Development of the Multi-Agency Safegaurding Hub (MASH) | NCC Strategic Plan (2014-18) / Children, Young People and Families (CYPF) Plan (2014-16) | Help and Protection Plan | Teresa Godfrey, Group Manager, Social Work Services Merlin Tinker, Operations Manager, MASH & Early Help Unit | To implement the improvement plan for the MASH, Early Help Unit and Adult Access Service in order to continue to improve the service provided. Key aspects include: (1) the consistent and appropriate application of thresholds; (2) the undertaking of statutory assessments only when necessary, and for early help to be provided where appropriate; (3) the strengthening of the MASH partnership; (4) information sharing practice develops further; (5) the reduction in the numbers of inappropriate referrals; (6) the recording within the MASH is consistent and demonstrates best practice; (7) improve the quality of information about the MASH process for families and referrers; (8) to ensure all staff from all agencies in the MASH have up-to-date knowledge and skills | Improvement plan to be implemented by the end of March 2016 | * Percentage of referrals to the MASH leading to an itervention by Children's Social Care or Early Help Services * Internal audits demonstrate the the effective recording of information; the correct decisions being made with regard to thresholds and improved information sharing where appropriate between partners. * Rreduction in the number of inappropriate referrals