## Actions
| Department of Health and Social Care Requirement | Current Position | Requirement fully met (Y/N)? | Future Activity to fill gaps | Lead Officer
Theme 1: Preventing and controlling the spread of infection in care settings
Guidance on infection prevention and outbreak management
1 | Continue to implement relevant guidance and circulate and promote guidance to adult social care providers in the area, including for visitors | Review and implementation of guidance is coordinated by the Care Home and Home Care Strategic Cell and by the system-wide Care Home and Home Care Operational Oversight Group that feeds into the strategic cell. An online toolkit is in place for care homes. It is revised and updated regularly by system partners. Two bulletins per week are sent to all care homes to provide guidance updates, including information in response to identified concerns or issues regarding working safely during COVID-19. The Principal Social Worker and senior management within Adult Social Care have updated guidance for staff to include the Ethical Framework, person centred practice and advocacy. As part of the Corporate response to the pandemic, the Council ensures that as an organisation we are compliant with all relevant Covid guidance. | Y |  | Director of Public Health
2 | Directors of Public Health should work with relevant partners including Public Health England and local health protection boards to control local outbreaks and should refer to the Contain Framework | The Local Resilience Forum outbreak control cell meets daily across Nottingham and Nottinghamshire bringing together stakeholders from Local Authorities, Public Health England, Infection Prevention Control, Environmental Health, police, primary and secondary care, comms and more. A joint COVID-19 Health Protection board and Local Outbreak Control Engagement board are in place. The Local Outbreak Control Plan has been published and Incident Management Teams are established to manage outbreaks. | Y |  | Director of Public Health
3 | Support care homes, working with local partners to carry out learning reviews after each outbreak to identify and share any lessons learned at local, regional and national levels | Infection Prevention Control services provide proactive and reactive advice and support to improve practice following outbreaks. Learning is shared regularly with the Outbreak Cell and the Care Home and Home Care Operational Oversight Group. This informs further advice and support communicated to Care Homes through the twice weekly bulletins and online toolkit. | Y |  | Director of Public Health
Managing staff movement
4 | Distribute money from the Infection Control Fund, and submit returns on how the funding has been used in line with the grant conditions | A robust on line application process was put in place for the Infection Control Fund 1 &2 in line with reporting requirements, which were extensively promoted to providers. This was further supported by the Quality and Market Management Team (QMMT) who targeted providers who had not used their funds to encourage effective utilisation. The service has now put in place arrangements for two dedicated officers to support these services - they will advise/guide those providers who are unsure how to meet the conditions, with specific reference to the CQC Care Home tracker or CQC homecare survey. | y |  | Service Director Integrated Strategic Commissioning and Service Improvement
5 | Consult the guidance available on redeploying staff and managing their movement, and support providers in their area to access other initiatives – for example Bringing Back Staff | The Quality Market Management Team(QMMT) have used the twice weekly communications to providers to offer guidance around the deployment and 'Bringing Back' of staff and to provide guidance around the completion of the IPC requirements through the submissions to the Capacity Tracker. Support was given to home care providers to bring back staff and this was undertaken successfully by many agencies, which helped to maintain capacity. Where issues are raised in respect of any provider who is not following the guidelines, direct contact will be made and if the situation isn't rectified then contractual sanctions will be applied. The Authority reviews and supports workforce issues in the social care market jointly with colleagues in the CCGs and the Care Quality Commission (CQC). | Y |  | Service Director Integrated Strategic Commissioning and Service Improvement
6 | Continue to review contingency arrangements to help manage staffing shortages, within social care provision, through the winter, with the aim of reducing the need for staff movement | External providers are required to complete the NHS Capacity Tracker and local dashboard: https://www.gov.uk/government/publications/adult-social-care-infection-control-fund-round-2 This data is reviewed daily and responded to when intervention is required in the market. There is a requirement that providers have robust business contingency plans in place and these will be monitored and supported through the quality monitoring processes. Where homes have short term staffing issues as a result of testing or the need to self-isolate, support is initially given around the utilisation of agency support and if required there is a system wide staffing pool that has been established to provide temporary staffing cover. This has been utilised on a number of occasions. | Y |  | Service Director Integrated Strategic Commissioning and Service Improvement
7 | Provide clear communication to social care providers regarding the importance of implementing workforce measures to limit COVID-19 infection, signpost relevant guidance, and encourage providers to make use of additional funding where appropriate | Communications have been managed centrally through the LRF Care Home and Home Cell to ensure consistent messaging to providers. Communication with providers has been co-ordinated by a County Council officer. We have utilised the twice weekly briefing to emphasise the importance of implementing IPC guidance. We have been supporting providers to access the Enhanced Care Response Team. This was further reinforced through weekly calls. Where services have not attended the ECRT Training then we have targeted these providers. Regularly updated guidance has been circulated through the twice weekly communications. The County Council has developed a Sustainability Fund which has been repeatedly promoted to providers. The Council's Business Support Team have also provided advice and guidance regarding other sources of funding and are providing one to one support for any business who are financially at risk. Providers will receive weekly (or as appropriate) briefings/communications from the Local Authority (on behalf of all system partners) which will include signposting to all relevant/up to date guidance. Dedicated officers will work with providers to maximise the appropriate use of the additional funding. | Y |  | Service Director Integrated Strategic Commissioning and Service Improvement
8 | Actively monitor Capacity Tracker data to identify and act on emerging concerns regarding staff movement between care settings, including following up with care providers who are not limiting staff movement | The Quality and Market Management Team (QMMT) will review the data submitted by social care providers in the NHS Capacity Tracker and the local dashboard on a daily basis. They will respond to issues and developing trends from this data as required. Where there are concerns, the Provider will be contacted directly and support offered. Where this does not resolve the issue contractual sanctions will be applied, including suspension | Y |  | Director of Public Health
Personal Protective Equipment (PPE)
9 | Provide PPE for COVID-19 needs (as recommended by COVID-19 PPE guidance) when required, either through the LRF (if in an area where they are continuing PPE distribution), or directly to providers (if in an area where the LRF has ceased distribution) | The Quality and Market Management Team (QMMT) will have a focus on working with Care Quality Commission(CQC) registered providers to allow them to understand the importance of signing up to the DHSC Personal Protective Equipment (PPE) portal (including emergency supplies). The provider PPE data submissions will be reviewed daily in line with the current Government guidance. The quality monitoring process will review the level/standard of training and intensive support will be delivered as required. Throughout the Pandemic, robust systems have been in place across the County to identify shortfalls in PPE and to support collection or delivery through a distribution network. Although providers are now steered to the central PPE portal, there are still local arrangements in place to meet any PPE shortfalls. | Y |  | Service Director Integrated Strategic Commissioning and Service Improvement
10 | Report shortages to the LRF or to DHSC | The Council actively monitors provider PPE stocks and reports/supports where there are shortages. PPE shortages are monitored on a daily basis and escalated as required. An OPEL rating on PPE stocks is reported daily and considered at a senior internal systems review meeting. | Y |  | Service Director Integrated Strategic Commissioning and Service Improvement
COVID-19 testing
13 | Ensure positive cases are identified promptly, make sure care providers, as far as possible, carry out testing as per the testing strategy and , together with NHS organisations, provide local support for testing in adult social care, if needed | The Infection Prevention Control (IPC) service follows the Incident Management Plan developed for Care Homes and other similar settings. Care Homes advise of symptomatic cases promptly to IPC and/or Public Health England, and in- reach testing is arranged, provided by a supported swabbing service (ECRT). Support is provided for risk assessment, outbreak management, whole home testing for staff and residents on a rolling basis, as well as a reactive programme. | Y |  | Director of Public Health
14 | Actively monitor their local testing data to identify and act on emerging concerns, including following up with care homes that are not undertaking regular testing, as per the guidance | A weekly care homes outbreak working group monitors testing, as well as outbreaks, and co-ordinates responses. Concerns with access to testing are referred to the testing coordination centre for support. | Y |  | Director of Public Health
Seasonal flu vaccines
15 | Support communications campaigns encouraging eligible staff and people who receive care to receive a free flu vaccine | A detailed and funded NCC communications plan is being delivered through all channels, internal and public (print, social media, websites, newsletters, adverts, lamp-post banners, videos and training). This links closely with the work of the Integrated Care System and Clinical Commissioning Group communications teams to ensure consistency. The current process evidenced improved take up last year, however, unfortunately it does not enable ongoing monitoring until the end of the programme. Managers are therefore working closely with their teams to promote uptake. | Y |  | Director of Public Health
16 | Direct providers to local vaccination venues | Communications detailed on point 15 above direct providers and eligible residents to GP/pharmacies. All national and local communication is aligned to this communication. | Y |  | Director of Public Health
17 | Work with local NHS partners to facilitate and encourage the delivery of flu vaccines to social care staff and residents in care homes | Public Health (PH) attends the Integrated Care System (ICS) flu group to promote uptake of flu vaccines by social care staff. The County Council provides funding to encourage domiciliary care staff to get a vaccination during work time. PH are running an internal staff flu programme which targets frontline social care staff - there is a voucher and in-house clinic offer. PH are funding 'myth busting' staff training for targeted care homes. | Y |  | Director of Public Health
Theme 2: Collaboration across health and care services
Safe discharge from NHS settings and preventing avoidable admissions
18 | Jointly commission care packages for those discharged from hospital (including commissioning of care home beds). The local authority should be the lead commissioner unless otherwise agreed between the CCG and the local authority | A countywide Discharge Cell is in place with joint sub- groups reporting into it, responsible for: 1. improving the co-ordination and MDT decision making for individual discharge in the north and south of the county 2. focusing on mental health/dementia 3. performance and metrics to monitor against national and local targets and outcomes 4. market capacity and commissioning. Appropriate single and lead commissioning arrangements are in place both for commissioning individual support and also the strategic commissioning of services. | Y |  | Service Director - Ageing Well
19 | Establish an Executive Lead for the leadership and delivery of the discharge to assess model | The NCC Executive lead has been established (Service Director Ageing Well) and communicated across the system. | Y |  | Service Director - Ageing Well
20 | Establish efficient processes to manage CHC assessments in line with the guidance on the reintroduction of NHS continuing healthcare (as well as the discharge guidance), which includes extending the use of the Trusted Assessor Model and digital assessments | Joint local protocols have been revised to implement the national CHC guidance with new streamlined processes and virtual assessments to be undertaken using MS Teams. Regular system reviews of the process are planned to ensure it is effective. Key outcomes and targets are monitored. A joint plan has been developed for all Scheme One COVID-19 deferred assessments - there are approximately 1,400 County Council residents on this scheme 30% of which require CHC assessment. Joint agreement has been reached on the plan and funding for people requiring CHC assessment and recruitment to staff is underway. We are awaiting a system decision to identify a £297k Nottingham & Nottinghamshire ICS population funding gap for staffing resources to complete the other 70% of assessments. | N | Confirmation of system agreement on how the funding for social care staff to assess the (majority of) deferred people is due by 31st October. Once agreed, temporary staff will be sourced. Without this additional resource the LA will need to prioritise existing staffing to work with people based on risk level, so whilst some of these will include people on the deferred list there is no guarantee that the assessments of people who are currently funded by Scheme 1 NHS funds will all be completed by 31st March 2021. Active recruitment is underway for the LA Supply Staff Register in readiness for the funding to be resolved. | Service Director - Ageing Well
21 | Secure sufficient staff to rapidly complete deferred assessments, drawing on discharge funding but without negatively impacting on care home support | Staff recruitment to undertake the CHC work is underway with 6 temporary posts already filled and due to go through induction. Advert has gone out to recruit more staff onto the County Council’s Supply Register in preparation for the funding to be resolved for the other 70% of deferred assessments as per above cell (D20) | N | Actions as per above cell (E20). | Service Director - Ageing Well
22 | Work with partners to co-ordinate activity with local and national voluntary sector organisations, to provide services and support to people requiring support around discharge from hospital and subsequent recovery | Different local voluntary sector partners are engaged in the Integrated Discharge MDTs of the 3 acute hospital systems across Nottinghamshire. They include for example: CVS/Age Concern/Age UK. The Discharge Cell monitors fortnightly outcomes for people on Pathway 0. | Y |  | Service Director - Ageing Well
23 | LAs are required to provide appropriate accommodation for people who have been discharged from hospital, if their care home cannot provide appropriate isolation or cohorting facilities, as set out in the Adult Social Care Action Plan. Every local authority should work with their respective CCG, to ensure that they have safe accommodation for people who have been discharged from hospital with a positive or inconclusive COVID-19 test result. Discharge funding has been made available via the NHS to cover the costs of providing alternative accommodation | A COVID positive infection, prevention and control checklist has been implemented so that there is a list of care homes in Nottinghamshire that are able to safely admit residents. This checklist was developed and will be supported by both the Council and CCGs. All residents discharged from hospital will have to be tested before going back to their respective care homes. There is currently a limited list of homes with 'COVID positive beds'. The QMMT/CCG review the numbers of 'COVID' beds available and also review the list of care homes on a weekly basis. There are also discussions on-going regarding having 'block beds' in a small number of homes as a contingency. ADASS issued a letter on the 13 October informing Local Authorities of a need for designated homes/units for COVID positive admissions from hospital. The QMMT sent a list of IPC compliant homes plus any other homes who are able to admit COVID positive admissions to the CQC on 16 October. | Yes provision is in place, No funding is not resolved | Escalation of funding issue nationally via HE TCG because the NHS funding to provide alternative accommodation can only be claimed for named individuals, however, the commissioning of Designated Care Homes requires block funding to cover periods of deep cleaning and voids. Also escalated is request to review option for areas that already have local determination and inspection processes in place to be able to do this locally rather than CQC, as more 'live' and locally sensitive model. | Service Director - Ageing Well
24 | LAs should consider adopting the cohorting and zoning recommendations published by ADASS, working with providers. This should include ensuring early partnership discussions with providers, about the safety and feasibility of implementing these arrangements within their care homes | Local criteria have been agreed jointly with City and County Local Authorities, CCG and the Infection Control Team with regard to what care home providers must have in place for different types of transition into care homes for people who are/have been COVID positive. An OPEL dashboard gives live availability of homes able to meet these criteria and the numbers of beds available. An initial assessment is undertaken by the Infection Control Team/QMMT and ongoing assurance is provided through already established quality monitoring processes which are managed by QMMT. The QMMT support providers in sending out relevant guidance and also support care homes with the IPC COVID Compliant checklists which includes cohorting and zoning. | Y |  | Service Director - Ageing Well
Social Prescribing
25 | Work closely with SPLWs (social prescribing link workers) to enhance well-being for people impacted by health inequalities. | NCC, CCGs and District Councils are working together to support people to use community assets to enhance their well-being, through: 1 - Supporting health colleagues to ensure posts are recruited to in a timely manner. 2 - Teams building good working relationships with the SPLWs. 3 - Linking with ICPs to embed SPLWs. 4 - Evaluating the SPLW role to determine if outcomes are being met. 5 - Working with SPLWs to avoid unnecessary hospital admissions. E.g. 1 - a Social Worker worked with a SPLW linked to Age UK to support a person with alcohol/cognition issues. The SPLW supported GP involvement and arranged for an alcohol liaison worker to work with the person to build trust, ensure correct support, and make sure the person was not discriminated against due to their support needs. Support was provided regarding debt as the person lived in a deprived area. This intervention empowered the person and enabled them to have choice and control over their life and outcomes. E.g. 2 - a case was raised in the Gedling huddle by our SPLW, who advised a referral be put through for a woman with physical and mental health issues who was struggling to connect with anyone during Covid. Work was undertaken via CSC in relation to Meals at Home and OT equipment. A referral was also for Reablement intervention relating to isolation, managing her physical health, anxiety/mental health and to link in with community. Referrals were also made for assistive technology and life line. The support helped the woman to feel part of the community and in control of her physical/psychological issues which had a positive effect on her wellbeing. | N | Ensure that relationships between partners are strengthened so that information about community assets is shared and gaps in availability are identified. Ensure that SPLWs can access ASC information from Mosaic via the Health and Care Portal, to inform their work. Implement new proactive interventions via Healthscope so that SPLWs can carry out workflow tasks to refer identified people through to relevant available services quickly e.g. Carers Hub. | Service Director - Living Well
26 | Ensure SPLWs have the support and equipment to work remotely and access GP IT systems | Whilst it is noted that SPLWs are employed by Health and not the Council, Adult Social Care continues to work with partners to ensure that SPLWs can work remotely and have access to GP and other necessary ICT systems. | N | To work with Health colleagues and other agencies within Primary Care Networks to ensure that access to all ICT systems and information is available to enable role to be undertaken effectively. | Service Director - Living Well
Theme 3: Supporting people who receive social care, the workforce, and carers
Supporting independence and quality of life
Visiting Guidance
27 | Give a regular assessment of whether visiting care homes is likely to be appropriate, within the local authority or within local wards, taking into account the wider risk environment | Government guidance on visiting care homes is monitored daily and communications sent to care home providers as relevant, supported by weekly calls to all providers. System-wide work with the Infection Control Team etc is undertaken through the Outbreak Cell of the LRF, reporting into HETCG. This Cell works closely with the Care Home and Home Care Discharge Cell. Risk assessment guidance developed by the Principal Social Worker and the Principal Occupational Therapist is in place for professionals on when a visit into a care home is warranted e.g. to assess safeguarding referrals. | Y |  | Director of Public Health
28 | If necessary, impose visiting restrictions if local incidence rates are rising, and immediately if an area is listed as ‘an area of intervention’ | Visiting restrictions are discussed and reviewed on a minimum weekly basis at the LRF outbreak control cell. | Y |  | Director of Public Health
Direct Payments
29 | Consult the new guidance for the actions that should be undertaken to ensure that people receiving direct payments, their families and carers are able to meet their care and support needs this winter | 1. The department has communicated with all Direct Payment recipients to advise that Personal Assistants (PAs) are eligible for free flu vaccine. 2. A briefing has been provided for all DP recipients to advise that they can access free COVID related Personal Protective Equipment (PPE) from the Nottinghamshire County Council PPE portal. 3. Frontline teams have been advised to assess flexibility in the use of DPs during the COVID period (in line with the Government COVID Guidance for DP recipients). | N | 1. Once the guidance for people who are employed by a DP is updated by the Department of Health & Social Care , the Department will review this against our internal DP policy to understand if any actions are required to continue to maintain full compliance. 2. A Co-production Task and Finish Group has been set up to discuss the Government COVID Guidance for DP recipients and how to implement future requirements. | Service Director Integrated Strategic Commissioning and Service Improvement
30 | Give people with direct payments the level of flexibility and control as envisaged in the Care Act and NHS Direct Payment regulations and accompanying guidance, allowing them to stay well, and get the care and support they need | 1. The Department has communicated with teams (via the Practice Newsletter and through a direct e-mail to Team Managers) to advise them of the flexible use of Direct Payments (DPs) during the COVID period, and have encouraged creative use of DPs to meet outcomes. 2. DP guidance has been updated. | N | 1. If staff and members of the public get in touch with DP Enquiries regarding COVID related barriers to delivery, Direct Payment Quality Officers (DPQOs) will work proactively with the individuals to enable innovative problem solving. This will support flexibility and control to be retained by the DP recipient. 2. A Co-production Task and Finish Group has been set up to discuss the Government COVID Guidance for DP recipients and how to implement future requirements. | Service Director Integrated Strategic Commissioning and Service Improvement
Support for unpaid carers
31 | Make sure carers, and those who organise their own care, know what support is available to them and who to contact if they need help | The Council's Customer Service Centre and Notts Carers Hub continue to provide carers with appropriate information, advice and support through virtual means - interactive and web based. Reviews of carers are being undertaken on basis of those most likely to need additional or alternative forms of support. GP Practices are supported to identify carers and supply relevant information. Information is regularly shared through carer networks & services. Carer reviews are being prioritised for people who may need alternative services or where health and well being is most at risk. | Y |  | Service Director - Ageing Well
32 | Follow the direct payments guidance and be flexible to maximise independence | The Council's Customer Service Centre and Notts Carers Hub continue to provide carers with appropriate information about their options, including Direct Payments. Policy, processes and supervision are in place to ensure staff are compliant with DP guidance. 100% of Carers eligible for a Personal Budget currently take it as a Direct Payment. | Y |  | Service Director - Ageing Well
33 | Ensure that assessments are updated to reflect any additional needs created by COVID-19 of both carers and those in need of social care | Carers assessments and reviews are being prioritised for people most at risk due to Covid 19. 1,603reviews have been undertaken since June 2020. | N | Plans are in place to complete an annual review on a further 2,900 known carers. Work is underway with the CCG to put in place temporary additional services to support carers with Covid related issues e.g. support with mental health and well being. | Service Director - Ageing Well
34 | Work with services that may have closed, over the pandemic, to consider how they can reopen safely or be reconfigured to work in a COVID-19 secure way and consider using the Infection Control Fund to put in place infection prevention and control measures to support the resumption of services | NCC provider services continue to deliver support in line with COVID 19 guidelines. NCC Short Breaks are running at 50% capacity; all carers have now received a break and are continuing to be prioritised to prevent unnecessary admissions where carer stress is at its highest level. Day Services are delivering a transitional offer consisting of building based outreach and virtual support in line with assessed need. QMMT are working with external providers to support them to provide Covid secure services. These providers are included in the comms bulletin circulation list and also receive regular telephone support and guidance from QMMT officers. | N | Work is being undertaken to develop a COVID-19 secure interim short breaks and day opportunities model which will be in place by January 2021. This model aims to increase the range of available alternative breaks to support carers during COVID 19 including greater emphasis on shared lives. | Service Director - Living Well
35 | Where people who use social care services can no longer access the day care or respite services that they used before the pandemic, work with them to identify alternative arrangements that meet their identified needs | Contact is maintained with people and their carers to assess risk levels and immediate needs. Reviews of all carers are being undertaken to consider alternative support mechanisms to meet people's needs in the community and enable carer respite. Some day activities have been delivered via phone or online. Building based day opportunities were resumed in September at a reduced level to enable COVID measures to be in place. Carer stress is given priority and Direct Payments have been relaxed to give greater flexibility for people living in the same household to offer support . Carers Hub contact details are being promoted to encourage new carers to access advice and support. | N | Work is being undertaken to develop a COVID-19 secure range of opportunities by January 2021 which aim to increase the range of alternative breaks for carers. There will be a focus on shared lives being developed alongside a short term break strategy and a focus on a range of day opportunities. This work is governed and monitored through the Department's Transformation Board reporting into the Senior Leadership Team and through into Committee for policy decisions. | Service Director - Living Well
End-of-life care
36 | Ensure that discussions and decisions on advanced care planning, including end of life, should take place between the individual (and those people who are important to them where appropriate) and the multi-professional care team supporting them. Where a person lacks the capacity to make treatment decisions, a care plan should be developed following, where applicable, the best interest check-list under the Mental Capacity Act | The Nottinghamshire & Nottingham Integrated Care System End of Life workstream is in place and reports into the Care Home & Home Care Cell (CHHC). The CHHC Cell is monitoring the delivery of training for all relevant staff on Advanced Care Planning to confirm that there is a consistent use of the RESPECT tool for end of life care across the County. Where a person lacks capacity the most appropriate person in the MDT undertakes a Mental Capacity Act (MCA) assessment. The Council has refreshed it's MCA training and is rolling out to all appropriate staff this year. | Y |  | Service Director - Ageing Well
37 | Implement relevant guidance and circulate, promote and summarise guidance to the relevant providers. This should draw on the wide range of resources that have been made available to the social care sector by key health and care system partners and organisations including those on the NHS website and those published by the Royal Colleges of GPs | We have worked with system partners and are involved with the roll out of the ECRT Toolkit, much of which relates to End Of Life Support. Through the regular communications we have promoted EOL Training Sessions including the use of the RESPECT Tool and Verification of Death. On-going joint working with local Clinical Commissioning Groups/Health System partners continues to be critical to consistent messaging to the social care market in Nottinghamshire on the best use of resources in line with critical guidance. The Local Authority external workforce lead supports the social care market with there training requirements. The quality monitoring/data collection process continues to be important in evidencing the training requirements for the local social care workforce. | Y |  | Service Director Integrated Strategic Commissioning and Service Improvement
Care Act easements
38 | Only apply the Care Act easements when absolutely necessary | The process of Care Act easements has not been implemented in Nottinghamshire. The Local Authority has used the flexibility of the Care Act duties to ensure it continues to meet the needs of it's residents The process for Care Act easements has been agreed and will be reviewed should a decision to enact the easements be required in the future. | Y |  | ASCPH Corporate Director
39 | Notify DHSC of any decisions to apply the Care Act easements | The process of Care Act easements has not been implemented in Nottinghamshire. The Local Authority has used the flexibility of the Care Act duties to ensure it continues to meet the needs of it's residents. This would be the responsibility of the Corporate Director and Principal Social Worker to action if required. | Y |  | ASCPH Corporate Director
40 | Communicate the decision to operate under easements to all providers, people who need care and support, carers and local MPs in an accessible format | The process of Care Act easements has not been implemented in Nottinghamshire. The Local Authority has used the flexibility of the Care Act duties to ensure it continues to meet the needs of it's residents. The Council has developed a draft communication plan in the event that care act easements are required in the future. | Y |  | ASCPH Corporate Director
41 | Meet the needs of all people where failure to do so would breach an individual’s human rights under the European Convention on Human Rights | The process of Care Act easements has not been implemented in Nottinghamshire. The Local Authority has used the flexibility of the Care Act duties to ensure it continues to meet the needs of it's residents. | Y |  | ASCPH Corporate Director
42 | Follow the Ethical Framework for Adult Social Care when making decisions regarding care provision, alongside relevant equalities-related and human rights frameworks | The Ethical Framework for Adult Social Care is included in all relevant staff guidance. The staff guidance is available to all staff in Covid 19 practice support hub and updates are included in the Practice Newsletter which goes to all staff. | Y |  | ASCPH Corporate Director
43 | Work closely with local NHS CHC teams, to ensure appropriate discussions and planning concerning a person’s long-term care options take place, as early as possible after discharge | Adult Social Care has implemented a "discharge to assess" process across hospital settings where the long term needs of individuals are assessed and reviewed in the most appropriate setting after discharge from hospital. Joint local protocols have been revised to implement the national CHC guidance with new streamlined process and virtual assessments to be undertaken using MS Teams. | Y |  | ASCPH Corporate Director
Supporting the workforce
44 | Ensure providers are aware of the free induction training offer and encourage them to make use of it | The external workforce leads, working in partnership with the relevant organisations, will support the social care market in accessing any free training including the induction training. We have been working with ECRT system partners to support the comprehensive roll out of their training packages. The communication bulletin/provider forums will be utilised for sharing current training offers. The quality monitoring processes will target providers where there is a training need. | Y |  | Service Director Integrated Strategic Commissioning and Service Improvement
45 | Promote and summarise relevant guidance to care providers | Any new guidance is distributed to all providers through the twice weekly communications bulletins. Any further clarification is provided through weekly contact with the Quality Contract Managers and there is a generic e-mail to support any queries. Where there has been complex guidance, the Council have produced tools for providers to share with their staff in the form of Quick Reference Tools. We will continue to effectively maintain the communication bulletin and to utilise other communication forums available. | Y |  | Service Director Integrated Strategic Commissioning and Service Improvement
Supporting the wellbeing of the workforce
46 | Maintain, where possible, the additional staff support services which were put in place during the first wave of the pandemic | Adult Social Care have a Supply Staff Register in place to support demand if staff shortages occur which impact on well-being and will enable a rapid deployment of staff to wherever the need is identified. A further round of recruitment is underway to bolster this. There is also a system wide mutual aid workforce offer supported by a MoU in place monitored via the LRF Workforce Cell in liaison with the Care Home and Home Care Cell. | Y |  | Service Director - Ageing Well
47 | Review current occupational health provision with providers in the area and highlight good practice | The communication bulletin is there to share good practice with the social care market. Occupational therapy staff will continue to support providers with Moving and Handling risk assessment and advice, to ensure they maintain safe practice when working with people in their homes and when using specialist equipment. | Y |  | Service Director Integrated Strategic Commissioning and Service Improvement
48 | Promote wellbeing offers to staff and allow staff time to access support, as well as promoting to providers in the area | The Department has a Well being Action plan to help support the workforce to support their well-being and provide access to specific tools and services of use whilst living and working with Covid 19, for example, there is now a new self referral route for counselling. Guidance on individual risk assessments that includes specific advice to staff who may be more vulnerable to Covid is in place. The established quality monitoring processes for the external social care market will capture good news/practice (for example staff incentives). The communication bulletin/provider forums will be key in sharing 'news' with the social care market . Communication has been distributed to services around signposting to appropriate support for staff as well as advice and guidance in relation to staff wellbeing and welfare. | Y |  | Service Director Integrated Strategic Commissioning and Service Improvement
Workforce capacity
49 | Continue to review contingency arrangements to help manage staffing shortages within social care provision through the Winter | The NHS Capacity Tracker/local dashboard are reviewed daily to assess levels of risk in the workforce. There is a Local Authority daily OPEL dashboard report which indicates staffing shortages and other areas of risk in both internal and external social care services. Senior Managers use this data at daily Capacity and Flow decision making meetings to trigger deployment of available contingency options which are kept under review. Where a risk is identified the Local Authority will support providers to access support from the local hospital where there is the offer of bank care staff/nurses for emergencies. There is a Departmental Emergency Response Support Framework in place to support response to any emergencies arising. | Y |  | Service Director - Ageing Well
50 | Consult the guidance available on deploying staff and managing their movement, and support providers in their area to access other initiatives – for example Bringing Back Staff | All guidance is regularly reviewed and communicated to Providers through the twice weekly communication. This includes guidance around the deployment and 'Bringing Back' of staff and guidance around the completion of the IPC requirements through the submissions to the Capacity Tracker. A system wide mutual aid workforce offer supported by a MoU is also in place monitored via the LRF Workforce Cell in liaison with the Care Home and Home Care Cell. | Y |  | Service Director Integrated Strategic Commissioning and Service Improvement
51 | Consider how voluntary groups can support provision and link-up care providers with the voluntary sector where necessary | Low level support to individuals is available through the Nottingham and Nottinghamshire Local Resilience Forum (LRF) and COVID19 Community Support Hub, which co-ordinates support given by volunteers countywide. 1. Dependent upon the level of COVID restrictions, increased voluntary support will be required to prevent isolation and poor health and mental well-being. 2. Attendance at HAG (Humanitarian Assistance Group) to keep informed of current trends and evaluate effectiveness of demand vs availability. 3. To access the HAG to identify those most vulnerable requiring support in the communities which the LA are not involved with. 4. Ensuring that NCC website is updated to reflect how to access necessary support within the LA and wider stakeholders. | Y |  | Service Director - Living Well
52 | Support providers to complete the capacity tracker and update their adult social care workforce data set (ASCWDS) records to help ensure effective local capacity monitoring and planning | A daily review of the NHS Capacity Tracker/local dashboard is undertaken to support the social care providers where there is a possible risk to their workforce and we work closely with providers to complete the tracker. Out of 320 services only 5 homes are not regularly completing the tracker and these have been repeatedly targeted for compliance. The external workforce lead will support providers to complete the Adult Social Care Workforce Data Set (ASCWDS) as required by the Department of Health and Social Care (DHSC). Workforce issues are considered at a regular system wide forum that considers operational issues in the market and escalates issues to the Home Care and Care Home Cell. | Y |  | Service Director Integrated Strategic Commissioning and Service Improvement
Shielding and people who are clinically extremely vulnerable
53 | Local authorities will coordinate local support if shielding is reintroduced in a local area. This includes provision of enhanced care and support for CEV people on the shielded persons list | New guidance on shielding was issued in October 2020 by Central Government outlining shielding measures for each tier in relation to COVID-19 restrictions. Guidance will be followed by the LA and support provided to those who have had notification of being in the CEV group. Advice relates to - remaining at home for as much as possible; avoiding visiting the community in busy periods; avoiding unnecessary travel within and outside of their area and; working from home as far as possible. All risk assessments are in place and are reviewed in line with this updated guidance. | Y |  | Service Director - Living Well
Social Care work and other professional leadership
54 | Ensure that their social care teams are applying legislative and strengths-based frameworks (including those based on duties under the Care Act and Mental Capacity Act) and support partner organisations such as the NHS to do the same | The Council's Principal Social Worker, Principal Occupational Therapist and Group Managers have updated guidance to ensure it is consistent with our statutory duties and are ensuring that the Department's communications are consistent with our Strength Based Approach (SBA). Team Managers oversee the day to day work of our social care workers to maintain practice standards and statutory duties. In addition to this the PSW and the POT are communicating regularly across the department about all of these aspects of practice through the practice newsletter. Care Act refresher and MCA training is available for all staff through the My Learning My Career Portal. The department is also piloting an MCA online support community of practice. Multi disciplinary hubs and partnership working through the Local Resilience Forums provides support to health partners on Mental Capacity Act duties and SBA. The Council has also commissioned a strategic partner, Partners4Change, to support with their cultural change programme across the Adult Social Care Department to further imbed strength based practice. | N | With the support of Partners for Change (an external culture change partner), the department will be rolling out a Strengths Based Approach programme across the Department, commencing in November 2020. This is an ongoing programme of cultural change. | ASCPH Corporate Director
55 | Ensure social care practice is fully cognisant of and acts on the issues of inequality and deprivation and the impact this has on communities and people’s access to health and social care services | Reducing inequalities and deprivation is inherent in social care workers' practice. Team Managers have oversight of social care workers' day to day practice, and one to one supervision provides opportunities to escalate and address any issues of inequality and deprivation that Council residents may be experiencing. Social care workers are maintaining face to face contact with residents, where it is safe to do so with the use of Personal Protective Equipment (PPE) and complying with social distancing rules, to ensure they are hearing the voice of the person. The Nottinghamshire Health and Wellbeing Board strategy highlights areas of inequality in the county for the Council, Health colleagues and other partners to focus on. The department has reviewed the way we extract learning from complaints so these can be shared across the department to improve practice, these would also highlight any inequalities in service provision. The Association of Directors of Adult Social Services (ADASS) & Think Local Act Personal (TLAP) are undertaking a piece of research to review the impact of inequality and deprivation on residents in Nottinghamshire and Derbyshire. The Council will review the research undertaken by ADASS/TLAP once available. | Y |  | ASCPH Corporate Director
56 | Understand and address health inequalities across the sector and develop actions with partners, where required, taking into account the implications of higher prevalence of COVID-19 in Black, Asian and minority ethnic communities and inequalities experienced by people with learning disabilities, autistic adults, and people with mental health difficulties | Team Managers have oversight of social care workers' day to day practice, and one to one supervision provides opportunities to escalate and address any issues of inequality and deprivation that Council residents may be experiencing. Partnership working across the Local Resilience Forums (LRF) is providing increased understanding of health inequalities and the actions required to address these. The Adult Social Care department have developed a Race Equality Working Group to review our support to Black, Asian and minority ethnic communities. The department has worked corporately with the BME Network and the Disabled Employees Support Network to ensure we address concerns at work. The department is currently undertaking assessment and reviewing activity to ensure the needs of people are being met and we will ensure staff are considering the additional risks to these communities. | Y |  | ASCPH Corporate Director
57 | Review current quality assurance frameworks and governance oversight arrangements to ensure that winter and COVID-19 pressures do not reduce the ability to deliver high-quality social work practice | Quality assurance work around safeguarding activity has continued within the department. Quality assurance of social care work takes place as part of 1:1 discussions with managers, authorisation of budgets, progression frameworks and continuing professional development sessions. The department has reviewed the way we extract learning from complaints so these can be shared across the department to improve practice, these would also highlight any inequalities in service provision. We are reviewing our QA framework to include wider aspects of social work practice. | Y |  | ASCPH Corporate Director
58 | Develop and maintain links with professionals across the health and care system to ensure joined-up services | Partnership working across the Local Resilience Forum (LRF), the Integrated Care System and Integrated Care Partnerships is supporting a joined up approach across Social Care and Health. Multi disciplinary working is in place and is increasing the links with primary care colleagues - this has been further developed during the crisis to support the Discharge to Asses model across the County. | Y |  | ASCPH Corporate Director
59 | Lead local application of the Ethical Framework for Adult Social Care, ensuring that NHS partners fully understand their responsibilities to apply the ethical principles and values as part of discharge to assess delivery | The Principal Social Worker and senior management within Adult Social Care have updated guidance for staff to include the Ethical Framework, person centred practice and advocacy. Multi disciplinary working, as part of the discharge to assess model that is in place, provides some assurances of the Ethical Framework delivery. The department are currently undertaking an audit of hospital pathway 1 (home) discharge arrangements to review the decisions made. Team Managers have oversight of social care workers' day to day practice, and one to one supervision provides opportunities to escalate and address any issues of inequality and deprivation that Council residents may be experiencing. Quality assurance of social care work takes place as part of 1:1 discussions with managers, authorisations of budgets, progression frameworks and continuing professional development sessions. Person centred practice and use of advocacy is reviewed as part of our Quality Assurance activity. | Y |  | ASCPH Corporate Director
60 | Ensure that the application of new models and pathways are offering the best possible outcome for individuals, their families and loved ones, advocating for them and advising commissioners where these pathways cause a conflict | The department has embedded a new operating model across hospital discharge pathways which supports the delivery of better outcomes for individuals by assessing their long term needs outside of the hospital environment. Multi disciplinary working, as part of the discharge to assess model that is in place, provides some assurances of person centred outcomes. The department are currently undertaking an audit of hospital pathway 1 (home) discharge arrangements to review the decisions made, and to share learning. Care and support reviews are being undertaken to ensure person centred outcomes are being met during the pandemic. Our social care workers regularly engage with CCG commissioning colleagues to address any areas of conflict as part of their practice to advocate for people. We are also maintaining strategic links with our health commissioning colleagues via for example CHC Panels. | Y |  | ASCPH Corporate Director
61 | Review any systemic safeguarding concerns that have arisen during the pandemic period and ensure actions are in place to respond to them, enabling readiness for any increased pressures over the winter period | The department's Quality Market Management Team are providing support and assurance of the care market. The department's safeguarding training has been provided in an online format for social care staff. Governance through the Nottinghamshire Safeguarding Adults Board and the Adult Social Care Safeguarding Governance Group maintain effective safeguarding practice across services during the winter period. Quality assurance work around safeguarding activity has continued within the department. Learning from safeguarding activity is shared across the department via the practice newsletter and the NSAB web page, and for example specific training was arranged for staff around domestic abuse following the increased incidence during the Covid period. | Y |  | ASCPH Corporate Director
62 | Support and lead social workers and safeguarding teams to apply statutory safeguarding guidance with a focus on person-led and outcome focused practice | The department's safeguarding training has been provided via an online format for our staff to maintain their practice standards. We have also provided safeguarding eLearning for our relief staff and those staff who may have to be deployed. The department's safeguarding guidance focuses on ensuring a person centred approach and on meeting peoples outcomes. We have continued our safeguarding quality assurance work to ensure these practice standards are being met and any learning is shared with our social care staff via the practice newsletter. The Nottinghamshire Safeguarding Adults Board (NSAB) are meeting monthly to maintain a proactive approach and share learning across the system. | Y |  | ASCPH Corporate Director
Theme 4: Supporting the system
Funding
63 | Provide DHSC with information about how the money from the Infection Control Fund has been spent by 30 September 2020 | Required returns were submitted to the Department of Health and Social Care(DHSC) on 30 September showing allocation of all grant funding received to date (nearly £11.5m). | Y |  | ASCPH Corporate Director
64 | Continue to maintain the information published on the website regarding financial support offered to the local adult social care market | Required returns were submitted to DHSC on 30 September showing allocation of all grant funding received to date (nearly £11.5m). This information has been published on the Council's website. | Y |  | ASCPH Corporate Director
65 | Provide regular returns to DHSC on the spending of the extended Infection Control Fund in line with the grant conditions | Returns will be submitted monthly as required from November 2020 to March 2021. | Y |  | ASCPH Corporate Director
Market and provider sustainability
66 | Work with local partners to engage with the Service Continuity and Care Market Review, and – when requested – complete a self-assessment of the health of local market management and contingency planning leading into winter | As part of the COVID response, a range of LRF Cells were formed to manage a system wide approach. This includes a Care Home and Home Care Cell and a Discharge Cell. Both of these have a range of sub groups. These groups have been maintained and revised to support the system in relation to both COVID and Winter Pressures. This includes a Market Sustainability Sub Group. Issues are managed and escalated through risk logs and clear governance structures. The development of this group was informed by the involvement of a Military Liaison Officer and there continues to be military involvement. There are information sharing procedures/protocols with local partners (including Nottingham City/ regionally) which will be maintained or extended to assist in the timely identification of local risks and the development of effective local mitigation. This approach will also include the maintenance of local databases that identify developing commercial and quality risks in the social care market. The self-assessment survey has been completed with recommendations/actions incorporated into the Quality Market Management Team plan . | Y |  | Service Director integrated Strategic Commissioning and Service Improvement
67 | Continue to work to understand the local care market, and to support and develop the market accordingly | The needs of the market are monitored though a range of mechanisms which include: a local tracker that was developed to capture detailed market information in addition to that captured by the national tracker; the requirement to complete the national tracker; a risk matrix for monitoring care home sustainability using data from the tracker and other sources to predict and stratify care homes at risk; a large Quality and Monitoring Team with named links to each provider who carry out weekly calls and also proactively contact providers to address specific issues and concerns. All of this information is used to provide a detailed market picture which is shared system wide. There is currently twice weekly communication with the market through an extensive newsletter which has been agreed across system partners as the key communication platform. There are a range of provider events and forums and there has been an event at which the Corporate Director of Adult Social Care and local and national Public Health representatives met with providers in relation to IPC related issues. | Y |  | Service Director integrated Strategic Commissioning and Service Improvement
68 | Continue to support the provider market as needed, to secure continuity of care, including promoting the financial support available | The Council established a Sustainability Fund which is still operating to provide additional funds to providers experiencing COVID related costs. This has then been aligned to the IPC grant funding arrangements. The Council actively promotes the financial support available both at a local and Government level. Mechanisms have also been agreed, that where a care home is at risk of closure due to financial issues, that support may be offered to them in line with strict criteria. The market has also been supported in a range of other ways including the IPC Grant/PPE/completing the portal/ advice and guidance re visiting etc . There were daily communications (now reduced to twice weekly) to inform the market of any support or guidance available to them. | Y |  | Service Director integrated Strategic Commissioning and Service Improvement
CQC support: Emergency Support Framework and sharing best practice
69 | Work with the CQC to promote and inform providers about monitoring processes | The Authority has continued to work in partnership with the Care Quality Commission (CQC) through the already established information sharing processes (which include the ESF framework and sharing of good practice). Formal information sharing meetings take place with the CQC every 6 weeks. Where concerns regarding a provider are identified, these are immediately escalated to the CQC. Where meetings take place with providers regarding quality concerns, this is done in conjunction with CQC inspections and intelligence. Where there have been concerns re PPE use or other failures in infection control, the Council has acted as a conduit between the IPC Team and the CQC. | Y |  | Service Director integrated Strategic Commissioning and Service Improvement
Local, regional and national oversight and support
70 | Write to DHSC by 31 October confirming that a winter plan is in place and that work is ongoing with care providers in their area on their business continuity plans, highlighting any key issues if needed, in order to receive the second instalment of the Infection Control Fund. These plans should consider the recommendations of the national Winter Plan, and involve NHS and voluntary and community sector organisations where possible | The Quality Market Management Team (QMMT) will continue to work with providers to review/update their Business Continuity Plans with regular reminders in the weekly communication bulletin. Checks will be implemented during quality monitoring visits to gain assurance around the quality of those Continuity Plans. The QMMT will review its actions within the Winter Plan and update accordingly. The Senior Executive Officer will be writing to the DHSC to confirm that our Winter Plan takes in to account the recommendations of the national plan. Information about our proposed approach has been shared with NHS stakeholders and Healthwatch. | Y |  | ASCPH Corporate Director
71 | Continue current oversight processes, including delivery of Care Home Support Plans and engagement with regional feedback loops | The Quality Market Management Team (QMMT) is responsible for the on-going support/monitoring of social care services in Nottinghamshire. The team will maintain local and regional links with system partners. | Y |  | Service Director Integrated Strategic Commissioning and Service Improvement
72 | Continue to champion the Capacity Tracker and the CQC community care survey and promote their importance as a source of data to local providers and commissioners | The Quality Market Management Team (QMMT) is responsible for the on-going support/monitoring of social care services in Nottinghamshire. The team will maintain local and regional links with system partners. Providers are actively encouraged to properly utilise the tracker through the weekly calls and guidance has been given about specific elements which have not been appropriately completed. Before any IPC Grants were allocated, providers were required to demonstrate that they were using the tracker. | Y |  | Service Director Integrated Strategic Commissioning and Service Improvement
73 | Establish a weekly joint communication from local directors of adult social services and directors of public health to go to all local providers of adult social care, as a matter of course, through the winter months | There is currently twice weekly communication with the market through an extensive newsletter which has been agreed across system partners as the key communication platform. There has been an event at which the Corporate Director of Adult Social Care (DASS) and Public Health (PH) colleagues met with providers to discuss issues in relation to IPC. There have been specific communications to the market from the DASS and PH to address specific issues such as finance and infection control. | Y |  | ASCPH Corporate Director
Care home support plans
74 | To report on whether care homes are able to implement infection prevention and control measures | Through the One Version of the Truth System wide meeting, the service compliance around completion of the Infection Control Training is monitored. Where compliance is poor, Quality Contract Officers will make targeted contact with services to provide support and advice or manage through contractual sanctions. The Infection Protection Control (IPC) grant was proactively promoted to all care homes and was paid to all homes who requested it and met the criteria. Assessment tools are in place to identify homes who can manage COVID positive citizens. A tool has been developed by Contracting to give assurance that homes are following appropriate PPE guidance. Homes are asked to complete this where issues have been raised. | Y |  | Service Director Integrated Strategic Commissioning and Service Improvement
75 | Ensure care homes have access to support, including clinical support from primary care | As a system, clinical leads have been identified for each care home as nominated by the CCGs. These leads are linked to PCNs. Communication has been undertaken by the CCG with all care homes to inform them of this. This information is being monitored through the tracker and homes who are not yet identifying that they are aware of their clinical leads are being targeted with further information. | Y |  | Service Director Integrated Strategic Commissioning and Service Improvement
76 | Ensure there is an expanded offer of COVID-19 testing for all residents and asymptomatic staff | The testing of care homes for staff and residents is being managed centrally by PHE. Initially this was directly supported at a local level and this has now moved to providing support and advice where issues of access are raised or to manage the outcome of positive tests. The Quality Market Management Team(QMMT) monitor robustly the testing of clients/staff in care home settings and other social care services. Where either staff or residents test positive, Local Outbreak guidance is provided directly by NCC Public Health colleagues. Where there are large outbreaks, a process has now been implemented for carrying out a more extensive root cause analysis to inform current and future learning. | Y |  | Service Director Integrated Strategic Commissioning and Service Improvement
77 | Ensure that care homes have adequate supply of medical and personal protective equipment and training to use it effectively | The Enhanced Care Response Team (ECRT) have offered PPE training to care homes/home care agencies. The Quality Market Management Team (QMMT) have supported providers to have this training and continue to refer services for their support. The QMMT continue to work with system partners to understand the providers on-going requirements for training and equipment (and any developing shortfalls). | Y |  | Service Director Integrated Strategic Commissioning and Service Improvement