

Better Together

Working towards co-production across adult social care

# Our Action Plan for 2022-2023

|  |  |  |
| --- | --- | --- |
| **Area of work** | **Action** | **When** |
| **Listening Spaces** | Design plan for Listening Spaces with Senior Leaders | Spring /Summer 2022 |
| Start listening space programme | Summer/Autumn 2022 |
| Review learning and design next phase of Listening Spaces | Spring 2023 |
| **Projects** | Identify and advertise key co-production projects for 2022/23 | Spring 2022 |
| Start to share learning from co-production projects | Winter 2022 |
| Review progress and identify next projects | Spring 2023 |
| **Our Voice Co-production Group** | Advertise and recruit new members | Spring/Summer 2022 |
| Provide training for members | Summer / Autumn 2022 |
| Start to share ‘Our Voice’ news | Winter 2022 |
| Review progress and develop next steps | Summer 2023 |
| **Staff learning** | Launch chat forum for staff | Spring 2022 |
| Design staff toolkit | Summer 2022 |
| Explore and test options with IT colleagues for an online platform that supports working together | Autumn 2022 |
| Review progress and develop next steps | Winter 2022 |
| **Developing People** | Co-design policy for expenses / involvement payments | Spring 2022 |
| Co-design bank of people and carers with lived experience with voluntary sector partners | Spring/Summer 2022 |
| Co design and offer training to people and carers with lived experience | Spring/Summer 2022 |
| Review progress and develop next steps | Summer/Autumn 2022 |