## Sent 25.06.26
Via Project Number | Project Address | Project Description | Project Extents | Proposed Start Date
TP2601005 | Jermyn Drive, Arnold | Resurfacing | Whole road length | 2026-11-02
TP2601020 | B6028 Stoneyford Road, Sutton in Ashfield | Resurfacing | From B6023 Mansfield Road / Priestsic Road junction (incl. junction) to Ashfield Court | 2026-09-14
TP2601180 | Sir John Robinson Way, Daybrook | Resurfacing | From A60 to Nottingham Road | 2026-09-21
TP2601265 | Front Street Bus standings, Arnold | Resurfacing | Bus standings | 2026-09-07
TP2601275 | Kingsley Drive, Netherfield | Resurfacing | From Victoria Road to Rochester Avenue | 2026-09-07
TP2601295 | Victoria Road, Netherfield | Resurfacing | From Forester Street to Colwick Loop Road | 2026-10-05
TP2601380 | A60 Loughborough Road / Mere Way Roundabout, Ruddington | Resurfacing | Whole roundabout | 2026-09-14
TP2601905 | B6023 Mansfield Road, Sutton in Ashfield | Resurfacing | From B6023 Mansfield Road / Priestsic Road junction to Oak Tree Road. New Cross junction | 2026-09-14
TP2601920 | B600 Alfreton Road / Nottingham Road, Selston | Resurfacing | From surface change north of School Road to surface change at Annesley Lane | 2026-11-09
TP2601990 | Walker Street, Eastwood | Resurfacing | From Three Tuns Road to Lynncroft | 2026-10-19
TP2601240 | Layton Avenue, Mansfield | Resurfacing | From Rosemary Street to Stanton Place / Milton Street (Incl. Layton Burroughs) | 2026-09-10
TP2601260 | A60 Mansfield Road / Church Street, Market Warsop | Resurfacing | From surface change at Greendale Close to River View (Incl jnctn section of B6035 Church Street) | 2026-10-05
TP2601035 | A6117 Old Mill Lane, Mansfield (Section 1) | Resurfacing | From surface joint at Hallamway junction to surface joint at Barringer Road | 2026-10-05
TP2601045 | A6117 Old Mill Lane, Mansfield (Section 2) | Resurfacing | From surface joint at Barringer Road to surface joint approaching Sandlands Way R/bt | 2026-10-05
TP2601050 | A634 Sheffield Road, Blyth | Resurfacing | From B6045 Bawtry Road to 50 mph limits near Park Drive | 2026-10-12
TP2601060 | A638 London Road, Retford | Resurfacing | From Bacopa Drive to Bus stop layby just past the mini r/bt at Grove Road (Incl. both mini r/bts on this section) | 2026-10-19
TP2601080 | A57 Worksop Bypass (Southbound) | Resurfacing | From Gateford Road roundabout to Shireoaks Common roundabout - inbound (Southbound) | 2026-09-21
TP2601090 | A57 Worksop Bypass (Northbound) | Resurfacing | From Shireoaks Common roundabout to Gateford Road roundabout - outbound (Northbound) | 2026-09-21
TP2601095 | Grange Road, Blidworth | Resurfacing | From Saville Street to Lyndhurst Avenue | 2026-10-26
TP2601205 | A638 North Road, Retford | Resurfacing | From Hallcroft Road roundabout to approx 30m past Fulford Avenue | 2026-11-02
TP2601310 | Ransome Close, Newark | Resurfacing | Whole road length | 2026-11-23
TP2601325 | B6035 Sherwood Street, Market Warsop | Resurfacing | From surface joint at The Wickets to A60 Mansfield Road junction | 2026-10-12
TP2601365 | A617 Kirklington Road, Farnsfield | Resurfacing | From C49 Farnsfield Road to surface change at Kirklington Road (Willows Farm) | 2027-02-22
TP2601880 | B6045 Carlton Road, Worksop | Resurfacing | From Eastgate junction to B6045 Blyth Road junction | 2026-09-07
TP2601890 | A60 Doncaster Road / High Road, Carlton in Lindrick | Resurfacing | From Pinfold Drive to Hodsock Park Lane Byway | 2026-09-24
TP2601980 | C153 Shireoaks Common, Shireoaks | Resurfacing | From o/s no 10 Shireoaks Row near canal bridge to the A57 R/bt | 2026-09-21
TP2601995 | A60 Doncaster Road / High Road, Carlton in Lindrick | Resurfacing | From approach to bend at Red Lane to Pinfold Drive | 2026-09-24

## Sent 15.07.26
Via Project Number | Project Address | Project Description | Project Extents | Proposed Start Date
TP2601935 | A608 Cordy Lane, Underwood | Resurfacing | From Willow Court to surface change o/s Nº 103 / Interactive speed sign | 2026-11-23
TP2601915 | B6020 Chapel Street, Kirkby in Ashfield | Resurfacing | From B6018 Sutton Road to Wheatley Avenue | 2026-11-23
TP2601082 | B6020 Lane End / Urban Road, Kirkby in Ashfield | Resurfacing | From Railway bridge to Portland Street | 2026-11-30
TP2601945 | C85 Annesley Lane, Selston | Resurfacing | From M1 Bridge to B600 Nottingham Road | 2026-11-23
TP2601925 | C85 Salmon Lane, Annesley Woodhouse | Resurfacing | From Skegby Road to M1 bridge | 2026-10-26
TP2601985 | A57 Markham Moor A1 Bridge North (A638) roundabout | Resurfacing | Full roundabout | 2026-11-16
TP2601965 | A614 Bawtry Road, Bircotes (Phase 1) | Resurfacing | From surface change near derestriction at Elm Cottage to a point approx 300m beyond Snape Lane travelling North | 2026-10-26
TP2601975 | A614 Bawtry Road, Bircotes (Phase 2) | Resurfacing | From surface change north of Snape Lane to Hawk's Nest | 2027-02-01
TP2601052 | York Terrace, Market Warsop | Resurfacing | Whole road length | 2026-11-30
TP2601006 | B5010 Derby Road, Stapleford | Resurfacing | From Toton Lane junction to surfacing joint at Hall Road | 2027-01-18
TP2601002 | B600 Main Road / Watnall Road, Watnall | Resurfacing | From surface joint approx 50m north of Common Lane (end of layby) to Little Holland Gardens | 2027-01-18
TP2601004 | Main Street, Newthorpe | Resurfacing | From B6010 Beauvale past Greenacres to surface change near bend at No 202 | 2026-10-19
TP2601014 | A60 Mansfield Road, Arnold | Resurfacing | Surface change at the Ram Inn nr Henry Street to surface joint at Arch Hill Layby | 2026-09-28
TP2601016 | A60 Mansfield Road, Woodthorpe | Resurfacing | From junction at Woodthorpe Drive to junction at A6514 Valley Road | 2027-02-08
TP2601008 | Birchfield Road, Arnold | Resurfacing | From Oakdale Road to Homefield Avenue | 2027-02-15
TP2601026 | Godfrey Street, Netherfield | Resurfacing | Whole road length | 2027-01-11
TP2601018 | Gunthorpe Road, Gedling | Resurfacing | From Stanhope Road to Bayliss Road | 2027-02-01
TP2601022 | Hilton Road, Mapperley | Resurfacing | Whole road length | 2027-03-15
TP2601012 | Killisick Road, Arnold | Resurfacing | From Gleneagles Drive to Parry Way | 2026-10-26
TP2601028 | Valley Road, Carlton | Resurfacing | From Marshall Hill Drive to Foxhill Road | 2027-03-01
TP2601024 | Whittingham Road, Mapperley | Resurfacing | From Haywood Road to Kent Road | 2027-03-22
TP2601062 | A6075 Forest Road / Tuxford Road, Ollerton | Resurfacing | From surfacing joint at Briar Road to B6387 Main Road | 2027-03-01
TP2601064 | C13 Bilsthorpe Road / Main Street, Eakring | Resurfacing | From 30 limits (Layby) entering Eakring to Kirklington Road | 2027-02-01
TP2601078 | C4 Gotham Road / Lantern Lane Roundabout, East Leake | Resurfacing | Whole roundabout | 2027-03-15
TP2601036 | A6075 Debdale Lane / A6075 Priory Road, Mansfield | Resurfacing | From A6191 Chesterfield Road North to mini r/bt at Church Hill (Inc. mini R/bt) | 2027-02-01
TP2601315 | A617 / A6191 Chesterfield Road North, Pleasleyhill Way junction, Pleasleyhill | Resurfacing | From start of central reservation approaching signals to o/s no. 346 - Inbound lane towards Mansfield. | 2026-10-23
TP2601955 | A60 Doncaster Road, Langold | Resurfacing | From Hodsock Park Lane Byway to A634 Oldcotes | 2026-09-21
TP2601385 | C83 Drove Lane, Newark | Resurfacing (Insitu) | A46 / A1133 Winthorpe R/bt to the A17 | 2026-10-05

## 07.10.2026
Via Project Number | Project Address | Project Description | Project Extents | Proposed Start Date
TP2601195 | Station Road / Forest Street, Sutton in Ashfield | Resurfacing | From A38 junction to Outram Street | 2027-01-15
TP2601025 | A60 Nottingham Road, Mansfield | Resurfacing | From Baum's Lane junction to B6030 Forest Road junction | 2027-01-27
TP2601088 | Outram Street, Sutton in Ashfield | Resurfacing |  | 2027-01-23
TP2601965 | A614 Bawtry Road, Bircotes | Resurfacing | From surface change near derestriction at Elm Cottage to a point approx 300m beyond Snape Lane travelling North | 2027-03-05
TP2601042 | Priory Square / Station Street / High Street, Mansfield Woodhouse | Resurfacing | From Rose Lane to A6075 Debdale Lane junction | 2027-02-19
TP2601078 | C4 Gotham Road / Lantern Lane Roundabout, East Leake | Resurfacing | Whole roundabout | 2027-03-15